## Administrative Tasks
Category | When | Task | Expanded Notes
Administrative Tasks | When Approved | Enter class on website calendar | Ensure accurate details: date, time, instructor, CE credits, registration link.
Administrative Tasks | After Posting Online | Notify CRD of relevant courses | Include course link, instructor name, date/time, CE availability.
Administrative Tasks | After Posting Online | Notify REBI of relevant courses | Same as CRD—use a pre-drafted template.
Administrative Tasks | After Posting Online | Create PDF and JPG/PNG marketing assets | Include course details, instructor bio, testimonials, and export in multiple formats for social/email.

## Advertising Tasks
Category | When | Task | Expanded Notes
Advertising Tasks | After Posting Online | Email Brokers marketing materials | Include attachments or Dropbox link and forwardable agent-facing copy.
Advertising Tasks | 30 Days Before | Email blast to agents | Write a compelling subject line and preview course benefits.
Advertising Tasks | 30 Days Before | Email instructor reminder | Confirm logistics, tech needs, and collect intro video.
Advertising Tasks | 25 Days Before | Email agents with instructor video | Embed thumbnail and strong CTA for registration.
Advertising Tasks | 21 Days Before | Post in FB group & run FB ad | Target real estate licensees nearby. Use a carousel or video testimonial.
Advertising Tasks | 14 Days Before | Email agents with testimonials | Use outcomes-based testimonials. Keep it short and visual.

## Pre-Class Processing
Category | When | Task | Expanded Notes
Pre-Class Processing | 7 Days Before | Send roster to instructor | Include a sample welcome message for them to customize.
Pre-Class Processing | 3 Days Before | Create books and materials | Include CE forms, printed slides, evaluation sheets. Prepare 10% overage.
Pre-Class Processing | 1 Day Before | Send Pre-Class email to students | Include all logistics: time, location/link, parking, what to bring.
Pre-Class Processing | 1 Day Before | Set up room or coordinate with office | Check AV setup, Wi-Fi, signage, and refreshment setup.
Pre-Class Processing | 1 Day Before | Print tent cards | Large fonts, sorted alphabetically, backup blank cards ready.

## Day of Class
Category | When | Task | Expanded Notes
Day of Class | 1 Hour Before | Open office & register attendees | Have sign-in sheets, badge stickers, and coffee ready. Test AV again.

## Post Class
Category | When | Task | Expanded Notes
Post Class | Day After | Collect all class paperwork | Check for completeness: signatures, rosters, CE forms, tests.
Post Class | Day After | Submit NAR roster to REBAC/REBI | Follow template, confirm student info is complete.
Post Class | Day After | Send feedback forms to instructor | Highlight positive quotes and trends in the feedback.
Post Class | Day After | Submit DPOR CE forms | Keep receipt confirmations for compliance tracking.
Post Class | Day After | Scan/upload all docs to Dropbox | Organize folder by year > program > course name.